## Sheet1
Task | Start | Days to Complete
Selecting a Topic | 2022-06-27 | 1
Researching on Topic | 2022-06-28 | 2
Requirement Gathering | 2022-06-30 | 1
Implementaion | 2022-07-01 | 7
Discussion with Guide | 2022-07-08 | 2
Report Making | 2022-07-11 | 2
Project Submission | 2022-07-13 | 2
44739
44755